CONSTRUCTION OF SIGNATURE BRIDGE BETWEEN OKHA AND BEYT DWARKA IN GUJARAT STATE-A CASE STUDY

Deepak Singla

Director-S.P.Singla Constructions Private Limited, INDIA

Rajiv Ahuja

Technical Advisor- S.P.Singla Constructions Private Limited, INDIA

Contact: rahuja2155@gmail.com

# ABSTRACT

A Signature bridge, known as the Sudarshan Setu is a cable stayed bridge with a length of 900m comprising central span of 500m and side spans of 200m each including approach spans has been  constructed connecting  Okha on the main land and Beyt Dwarka island in the state of Gujarat. The overall length of the bridge is 2320m including approaches. The pylon height is 130m and each pylon leg is supported on pile foundation. The deck width is 27.2m which includes divided carriageways of 9.5m width each and 2.5m wide covered footpath on each side. Constructing this bridge over a sea creek posed several challenges. This paper describes the salient features of the Cable stayed bridge and construction methodology adopted and the challenges faced.

Keywords: Piles; pile foundation; pylon; steel deck; stay cables; stressing; erection traveller

# 1. INTRODUCTION

Government of India, Ministry of Road Transport and Highways has constructed a 4 lane Signature Bridge connecting missing link between Okha and Beyt Dwarka on EPC mode including construction of approaches on new NH 51 in the state of Gujarat. Beyt Dwarka, located on the western coast of India is famous for its archaeological, historical and spiritual importance and is better known for Dwarkadhish Temple. However, the Beyt Dwarka was inaccessible by road being an island and Dwarka is located near port Okha, which is an all-weather minor port. The people from all over the country and from outside visit this pilgrim place and they had to use the passenger ferry service operated by Gujarat Maritime Board near Okha port to reach this Island.

To obviate this problem, The Government of Gujarat decided to join Beyt Dwarka by land by providing a bridge from Okha to Beyt Dwarka. Ministry of Road Transport and Highways had awarded the project[1] to S.P. Singla Constructions Pvt. Ltd. (SPS). The bridge is meant to provide direct road connectivity from Okha to Beyt Dwarka and provides pedestrian lane also so that pilgrims coming to Beyt Dwarka on foot can avail this bridge. Index plan of the site and bridge location are shown in Fig. 1 and Fig. 2 respectively.

The construction contract was awarded to S.P.Singla Constriction Private Limited on 19th March 2018 and the construction had commenced in August 2018. The bridge was opened to the traffic in February 2024.

Constructing the Cable stayed bridge with a span of 500m, which is largest span constructed in India so far, posed huge challenge in construction in a marine environment.

# 2. PROJECT DETAILS

The Signature Bridge connecting Okha port and Beyt Dwarka is 2320 m long. A length of 900 m long three span cable-stayed bridge is provided in the central portion of Signature Bridge having main span of 500 m (main navigation span) with two side spans of 200m each.  Approach roads of 2.452 km length (1 .241 km on Okha side and 1.211 km on Beyt Dwarka Side) are developed as a four-lane divided carriageway highway along the project stretch. Fig.3 shows the Layout of the project including side spans and approach roads[1].

Pylons for cable stayed bridge are constructed as modified A-shape and cable arrangement is semi-fan type and provided in two planes. Vertical clearance of 18 m is provided below navigation span as per coast guard requirement. For remaining portion of the bridge, span length is kept 50 m and minimum vertical clearance above HTL is provided as per relevant IRC code.

The 27.2m wide bridge deck comprises of 4 lane vehicular carriageway (9.5m + 9.5m) with a central median of 1.2 m & two separate corridors of 2.5 m clear width each for golf cart/cycle track/pedestrian walkway respectively [2].

Fig. 1 Location of Beyt Dwarka Island

Fig. 2 Bridge Site Location

Fig. 3 Layout of the Signature Bridge and Approaches

Main features of the cable stayed bridge [2] are as follows:

- Pylon shape: A-shape having leaning configuration in outward direction having a height of 132m.

- Approach spans:

Okha side Length= 14 x 50m + 2 x 23.5m + 23m = 770m

Beyt side  Length= 11 x 50m + 4 x 25m = 650m

b) Minimum concrete grade for Pylon and its foundation/substructure is M70.

c) Superstructure Steel deck comprising edge beams and cross girders with Precast RCC deck in M70.

d) The bridge gradient limited to 1 in 50 so that it causes minimum discomfort to pedestrians.

e) Decorative Structural Steel Railing and Crash Barrier.

f) Impression of Peacock's feather of size 20m x 12m provided at top of Pylons.

g) Lightening arrester installed on top of pylons.

h) For protecting the structures in marine environment, suitable preventive measures against corrosion applied during concrete mixing, placement, surface coating to all exposed concrete surfaces, treatments to reinforcement, prestressing steel & structural steel provided as required.

i) Concrete wearing course along with appropriate water-proofing membrane provided for main carriageway as well as for golf cart/cycle track/pedestrian walkway for the entire bridge length.

k) Solar panels have been installed on the roofs of both sides of the pedestrian corridor, capable of generating 1 MW of electricity.

l) A total of 232 panels, evenly distributed at 10-meter intervals and featuring inscriptions relating to the life events of Lord Krishna are positioned along one side of the pedestrian corridor (Fig. 4).

m) Decorative Lighting: An advanced 3D lighting system has been implemented on the main bridge, capable of producing 99 distinct themes. This comprehensive lighting setup covers the pylons, stay cables, and bridge deck.

n) Viewing Galleries: A total of 12 viewing Galleries have been positioned on the bridge. 4 viewing galleries at Pylon location and 8 cantilever viewing galleries at Approach bridge locations (Fig. 5).

Fig. 4 Pedestrian Walkway and Panels featuring inscriptions

Fig. 5 Viewing Galleries

The main bridge has a span configuration comprising 500m central span and side spans of (50m+50m+100m=200m) on each side [2] as shown in Fig. 6. The cross section of superstructure in the main cable stayed span is shown in Fig.7.

Fig.6 Elevation Main Bridge

Fig.7 Superstructure Deck Cross section -Main Cable Stayed Bridge

Each pylon is supported on a huge pile cap of size 29m x18.5m x 4m which is supported on 22 nos. of 1.8m diameter cast-in-situ bored piles as shown below in Fig.8 & Fig. 9. Pylon is A-shaped leaning outwards having a height of 130m. Cross-section of pylons is a rectangular hollow box section with outer dimensions of 10m x 4m at the base.

Fig. 8 Pile Cap below each Pylon leg

3. CONSTRUCTION OF CABLE STAYED BRIDGE AND CHALLENGES:

At the time of construction, the central span of 500m was the largest span being constructed in India. It was a tender requirement that the pile caps should be cast below the high tide level which posed huge difficulties in construction. Considering the tight completion schedule, it was decided to construct four main pile caps of pylons above the High Tide level (HTL) and all the remaining pile caps of viaduct were cast below HTL. The construction methodology and challenges faced during piling, construction of piles caps, construction of pylons and erection of main span superstructure are described below.

Fig. 9 Cross section showing Pile Foundation and Lower Pylon

.

## 3.1 Piling

Cast-in-situ piles of diameter 1.8m and length of 48m at P4 pylon and 62m at P5 pylon were constructed by using a Jack up Barge for providing a stable drilling platform at piling locations. It took about 3 days to complete one pile and 155 days to complete the 22 piles below each pile cap including shifting of Jack Up barge and time lost in tidal variations etc. Concrete is transported to pile locations through Transit Mixers mounted on self-propelled Barges which feed the concrete to Boom placer placed on the barge, positioned near the piles to be cast. Liners of 8 mm thickness were driven approx. 5m into the sea bed using rig machines and crane, up to height of the level of the Jack up platform. Rebar cages were pre-fabricated at the rebar yard and then transported to pile location through Barges and were lowered using 75MT capacity crane. Fig. 10 shows the piling operation.

3.2 Pile Cap Construction

Bottom shuttering for Pile caps of Main Pylon were in the shape of Pre-cast Slabs supported  on the top of steel brackets welded to liner of already cast Piles. The gap between the sacrificial slab and Pile liner was filled with cast in place non shrink concrete (GP2). The sacrificial slab was cast in casting yard near sea shore where the floating barge could be placed during high tide. Sacrificial slab after casting is transported and placed in the position with the help of suitable capacity of crane mounted on floating barge. This methodology was adopted to minimize the works on the marine site, reduce the construction period, avoid process of shuttering and de-shuttering in water and improves the constructability of structure.

Fig. 10 Pile Construction through Jack Up Barge

Pile caps for an offshore bridge were constructed according to sequence given below:

1) Installation of steel bracket on liner of already cast piles (Fig.11)

2) Surveying of pile center point after Casting.

3) Casting of Sacrificial slab.

4) Transportation & Installation of sacrificial slab (Fig. 12).

5) Chipping of pile head.

6) Transportation & fixing of Rebar.

7) Fixing of shutters.

8) Pouring of concrete for Pile cap (Fig.13 and Fig. 14).

9) Construction of connecting beam.

Fig.11 Steel bracket welded with liner

Fig.12 Lifting and Placing of Sacrificial Slab at location

Concrete of grade M70 is transported to the location by barge mounted transit mixers with boom placer. Concrete was laid in four lifts of one meter each with 300mm layers and compacted with 60mm needle vibrator.

Fig. 13 Showing Construction of Pile Foundations

Total time taken for reinforcement binding, fixing the shuttering and concreting of pile cap was about 80 days. The time taken for concreting of pile cap alone was 4 days.

Fig. 14 Casting of Pile Cap

3.3. Construction of Pylons:

Pylon shape is A-type with leaning outward configuration with an overall height of 132 m as shown in Fig. 16. After construction of Pile cap, Tower crane is installed at proper place on top of pile cap for construction of Pylon leg. DOKA automatic climbing formwork was used for the construction of pylon legs, designed for adjusting to the leaning configuration geometry. The sequence for casting of pylons adopted is as follows:

a. Construction of Pylon legs up to 6.8 m height above the pile cap.

b. Construction of lower cross beam at level 6.8m above the pile cap.

c. Construction of pylon legs up to 69.1m (Bottom of upper cross beam)

d. Construction of upper cross beam at level 69.1m.

e. Construction of pylon up to 91.15m including placing of six anchor boxes.

g. Construction of legs of Pylon up to 132m height in 3.5 m to 4m lift each.

h. Cable inserting and stressing as per given schedule.

Fig. 15 shows the construction of lower pylon.

Fig.15 Casting of Lower Pylon legs

Fig. 16 Pylon Shape

## 3.3.1 Casting of Lower Cross Beams

Concreting of lower cross beam including its soffit slab, vertical walls and top slab could be done independently in parallel to casting of pylon legs up to 36m. Lower cross beam is not cast for the full length; a small gap is left in the middle of lower cross beam. After the concrete attains required strength, lower cross beam is jacked apart by placing jacks between shear keys by 800tons and closure segment is cast. Again, after required strength of closure segment is achieved stressing of lower cross beam is done. All this process of construction of lower cross beam took around 45 days. Fig. 17 shows casting of lower cross beam.

Fig.17 Casting of Lower Cross Beam

## 3.3.2 Construction of Upper Cross Beam (UCB)

After constructing both legs of pylon up to 69.1 m arrangement for shuttering for upper cross-beam is done on previously embedded bolts in walls of pylon legs at required height.

Fig. 18 Installing Strut at 44 m height Beam                 Fig. 19 Construction of Pylon and Upper Cross Beam

Special truss arrangement was made on brackets fixed on pre-embedded bolts and bottom shuttering arrangement was done using ISMB and steel shutters. The height of upper cross beam is 4.5 m. After concreting of upper cross beam is completed strut fixed at 44m height to maintain gap between legs of pylon is removed. Fig. 19 shows the construction of Pylon including upper cross beam.

## 3.3.3 Construction of Pylon up to top

This is the most critical phase of construction as all the cable anchorage system, steel anchor boxes to hold anchorage system, Peacock feather impression on walls of pylon and superstructure construction will start with this phase. Fig.20 shows the casting operation of pylon up to the top.

Specialized modifications on outer shutters for constructing peacock feather on walls was done. The pylon was cast up to 91.15 m in six different height lifts above the upper cross beam. Prefabricated steel box structures with guide pipe arrangement for holding of anchorages of stay cable are positioned inside the walls. After fixing, survey for checking position of inside shutters and guide pipe alignment is done.

Fig. 20 shows the fixing of anchor boxes inside the pylon and Fig. 21 shows construction of pylon.

Fig. 20 Installation of Anchor Boxes inside the Pylon

During construction of pier between upper cross beam and 91.15m height of pylon leg, pier table segment is launched and Erection gantry for superstructure erection is assembled on pier table. After installation of pier table and erection gantry, construction of pylon and superstructure was done in parallel. After construction of pylon up to 91.15 m, 1st segment of superstructure on both main span and back span side is constructed.

After each activity of superstructure i.e., lifting of segments, 1st stage stressing, placing of precast deck slabs and final stressing, survey for pylon position is done. This process is repeated after every segment of superstructure launching and construction of pylon leg. After launching of 1st segment pylon construction up to height of 94.65m is completed and then 2nd segment of superstructure is launched and completed in all respects. Same procedure for each lift of pylon and each segment of superstructure is followed up to top of pylon leg. After 2ⁿᵈ segment of superstructure, one lift of pylon is cast and after that 3ʳᵈ segment of superstructure is erected. Again, one lift of pylon is cast and 4ᵗʰ segment of superstructure is erected. This procedure is continued up to construction of top of pylon and erection of 12ᵗʰ segment of superstructure. Same procedure of reinforcement, shuttering, concreting and survey is adopted for construction of pylon leg up to top. Once the construction of pylon is completed all remaining segments for superstructure were installed as per construction procedure of superstructure. Time taken for completion of each pylon was about 780 days approximately.

Fig. 21 Casting of Upper Pylon

# 4. CONSTRUCTION OF SUPERSTRUCTURE:

The superstructure cross-section is shown in Fig.7. There are 20 deck segments of 12m length approx. for the main span and 21 segments for the side span on either side of each pylon and the closure segment length is 3m. There are 3 pier table segments on each pylon, thus the total number of segments erected is 89. Each segment has longitudinal edge beams with three intermediate cross girders assembled in a workshop and transported to the site on barges. An erection gantry of about 24.88 m length was deployed for the erection of the deck’s steel beams. Half of its length of the gantry’s pair of main trusses are located over and anchored to the previously erected deck segment and the remaining length is cantilevering over the next deck segment to be erected. The construction sequence for the main span mainly involves the following steps.

## 4.1 Steel Deck Erection:

After the pylon is constructed up to a height of 69.1m and the upper cross beam is constructed and stressed, the pier table segment (steel part) is lifted and installed over the temporary bearings/supports. Concrete slab is cast over the pier segment and erection traveler is installed over it. At this stage, the pylon and deck are constructed in parallel.

Segments of length 12m each along with cross beams, weighing 90 to 100 t were fabricated at Rajpura (Punjab) located 1550 KM from the Okha port. Once the segments reach the site, they are transported over a barge (Fig. 22) and are lifted by the erection gantry (Fig. 23) at bridge location. Each segment has stay cable anchorages and is bolted to the previously erected segment through splices. First the main span cable is stressed and then side span cable is stressed.

Fig. 22 Deck Segment being transported on barge                                     Fig. 23 Lifting of Steel Segment

Steel segments are lifted and erected on both sides of pylon and stay cables are stressed-first on main span side and then on side span side and precast deck slab is placed. Thereafter, the erection traveler is moved to the next position. Pylon is cast in lifts of 3.5m each and segments are erected on both sides and the process is repeated till full pylon height is constructured and all the segments are erected. The total number of segments erected was 89 including  42 nos. on both side spans, 41 nos.  on main span side and 3 nos. on each pier table of both the pylons. Geomeric control was exercised as per construction drawings and recommneded camber was provided during each stage of erection.

## 4.2 Stay Cables Installation and Stressing

In total there are 76 cables (38 on each side of pylon), with number of 15.7mm strands varying from 34 minimum to 73 maximum in the various cables, which are individually greased and protected by a tightly extruded HDPE sheathing. To provide mechanical protection of the cables’ mono strands, each cable is covered with an ungrouted high-density polyethylene (HDPE) pipe with double-helical ribs to reduce the risk of rain &  wind induced vibrations. The specifications for stay cables given in the Contract Agreement [1] and other applicable specifications as given in the international references [3],[4] were followed. The length of cables varies from 60.82 m minimum to 279m maximum. The cables are installed and stressed using the strand-by-strand installation and stressing method with the jacking operations occurring in the pylon. Fig. 16 shows anchorage locations.

## 4.3 Casting of Closure Segment

Construction of the closure segment is always a difficult task and requires precision workmanship. A closure segment is fabricated after taking precise measurements from each side of erected main steel girders at the center of the main span over a few days to account for temperature effects. Once fabricated with precise dimensions and bolt holes, the closure segment is connected to both side main girders which also require some adjustment of levels achieved through loading the deck on the affected side. Fig. 24 shows the erection of closure segement.

Fig. 24 Erection of Closure Segment

Fig. 25 shows the erection of superstructure deck and Fig. 26 shows the completed bridge.

5. Construction Challenges:

Tidal Variation: Dealing with large fluctuating tides posed difficulties in constructing the foundation, especially pile caps of the approach and main bridge.

High Wind Speed: Working at heights for Pylons became challenging due to consistently high wind speeds.

Cyclones: The project had to contend with the threat of frequent cyclones affecting construction progress. Like Cyclone Gulab, Maha, Vayu, Taukte, Gati and recently occurred Biparjoy.

Low Draft: Limited sea depth hindered the movement of barges at critical location of bridge.

Monsoon Season: The heavy monsoon period further complicated construction activities

Pylon Pile caps: Casting of Pile caps of size 29m x 18.5m x 4m in a sea was a huge challenge.

Transportation of Segments from Rajpura (Punjab) for  a distance of 1550 KM to the site and then transportation on barges for erection.

6. Conclusions

The Cable-stayed bridge at Beyt Dwarka is the first such bridge in India with a central span of 500m being the largest span so far. Construction of pile foundations was a huge challenge considering the size of pile cap for the pylons. Construction of leaning pylons required precise geometry control at every stage. Transporting assembled deck segments from the fabrication yard located 1550 km from the site and then to the exact location on huge barges and also transporting transit mixers on barges posed its own logistic difficulties. Other challenges faced were tidal variation, high wind speed and disruption of work due to COVID-19 pandemic. However, facing all these challenges, the bridge has been  completed successfully.

Fig. 25 Erection of Superstructure deck

Fig. 26 Completed Bridge

6. Acknowledgements

The following agencies were involved for the design & construction of this bridge and the project could be completed due to their active participation and support in construction of this prestigious project in India:

- Client: Road & Building Department, Govt. of Gujarat and Ministry of Road Transport & Highways, Govt. of India

- Design Consultant for Cable stayed Bridge: WIECON Co. Ltd., Taiwan

- Design Consultant for Foundation and Substructure: ASC Infratech Pvt. Ltd., Noida (UP)

- Proof Consultant: WENZEL CONSULT, Austria

- Architect: STUDI BOXX, Mumbai

- FORCE Technology, Denmark for Wind Tunnel Test

- Stay Cable supply, installation and stressing: VSL

7. References

[1] Contract Agreement between S.P.Singla Constructions Pvt. Ltd. and MoRT&H.

[2] Construction drawings prepared by design consultant WIECON, Taiwan

[3] FIB bulletin 30, Recommendation, Acceptance of stay cable systems using pre stressing steels.

[4] PTI recommendations for stay cables